MEMORANDUM

To:

Distribution


From:

F. Dylla/gpw

Subject:
FEL Upgrade Project Weekly Brief – May 2-6, 2005

Date:

May 6, 2005

Highlights:

We are pleased to report that FEL delivered light for its first user tests since we commissioned the FEL Upgrade. This week we completed the re-certification of User Lab 1 that will be used for a rather continuous stream of users test over the next few months. The first user team was led by Prof. Rox Anderson from Harvard Mass General Hospital who spent the latter half of this week on experiments investigating differential heating of fatty vs non fatty tissue in the near IR range. This proof of principal worked beautifully to show that incident laser light at wavelengths corresponding to overtones of C-H vibrations (at 1.2 and 1.8 microns) could be used to differentially heat fat tissue. 

The results of these initial experiments will be used to plan subsequent measurements and analysis for the design of potential laser medical treatments for skin disorders and fat removal. The experiment used tunable IR light at power levels (20 watts cw and 100 watts pulsed) that are unavailable with any other light source. For the entire two days of this test the FEL operated on demand and without interruption using the broad-band cavity. 

Next week we have a user tests planned by the Dahlgren group on IR sensor damage effects followed by certification activities in the THz lab. 

In other activities we had some success in identifying noise sources in the FEL systems that will allow us to improve operations, and the optics group made additional progress with their optical mounting techniques and with the vendors that are completing the high power optics at 1 and 1.6 microns.

Management:

We had our monthly meeting on Monday with the WBS managers to summarize the cost, schedule and technical progress for April for the UV FEL project. A meeting was held with the project management staff on Thursday to review the April and year-to-date cost-performance data for the Navy IR FEL project. 

George Neil and Michelle Shinn attended this week’s semiannual review of JTO funded projects at JTO headquarters in Albuquerque. JTO is currently funding projects on our advanced drive laser, optical damage measurements and the test by the Dahlgren group that will begin next week. 

Papers are being prepared for the Particle Accelerator Conference to be held May 15-19, 2005, in Knoxville and the Navy FEL Workshop to be held on May 23-25, 2005, at Northrop Grumman in Newport News.

Operations:

   The first half of this week was spent refining the setup for 1.7 micron operation with a hole coupler and certifying the laser safety systems for the user run on Thursday and Friday.  We also did some more detective work on sources of noise in the accelerator.  The latter half of the week was dedicated to the Wellman lab user run in User Lab 1. 
   On Monday we tried out a new match to the wiggler obtained on Friday.  It lased a bit better than the configuration from last week but had a low BBU threshold.  We then modified it to run higher current.  Finally we did some studies of the gain and loss of the laser near 1.7 microns and also at 2.8 microns, both with the hole coupler.  Calculations and measurements show that the loss for 1.7 micron operation should exceed 20% if one is centered on the hole.  This is comparable to the gain and so we run slightly off-center to reduce losses.  At 2.8 microns the calculated losses are slightly less than the measured losses of 14%.  This is low enough that we can lase centered on the output hole.  The reason for the high losses at 1.7 microns is that we do not have a working deformable mirror assembly (DMA) for the broadband cavity right now.  Once we get a working DMA installed we can decrease the Rayleigh range in the cavity, which will increase the gain and reduce the losses.  This will allow much better lasing at shorter wavelengths.  We spent quite a bit of time looking for noise in the system.  Two sources came to light, one in the drive laser (pickup from the switching supplies on the laser lamps) and one on the master oscillator. We are looking at ways to reduce these noise sources. 
   One Tuesday we used Nobuyuki Nishimori's new emittance script to measure the Twiss parameters in the accelerator and improve the match to the wiggler.  This produced a very nice match and the laser lased better than it had to date.  We also commissioned the laser protection system with the new hutches in User Lab 1. 
   On Wednesday we finished all laser protection system certifications and User Lab 1 was ready for operations.  The lab was prepared for the experiment. 
   Thursday and Friday were spent providing 1.6 to 1.8 micron light to User Lab 1 for studies of the interaction of FEL light with pig skin.  The laser lased well.  The main problems we had were with diagnostics and running the laser close to threshold when low power was required.

WBS 4 (Injector):

The DC Photocathode gun is operational.

Polishing started on the first of the three segments that will support the ball cathode. Minor design work on the gun vacuum chamber continued this week. Electrode mounts were cleaned for the College of William and Mary as they continue to plasma-process several stainless steel samples for field emission suppression film studies. The anode-electrode gap in the high voltage test stand was set this week by Survey and Alignment. Everything is ready for high voltage testing of the electrode coated with the field emission suppression film two times thicker than previously tested.

A poster on the performance of the photocathode gun was prepared this week for the upcoming PAC conference.

The latest LANL PARMELA version has been installed and the 100 mA injector deck is under testing. Simultaneously, the Superfish field maps are being converted to the format of the FEL-CEBAF PARMELA version so that we can eventually model the 100 mA injector in the two versions.

WBS 5 (SRF):

· AES and the Navy have signed a contract authorizing funding for the SRF gun related tasks.  This development will allow AES to move forward on engineering procurement of the remaining components for the 100 mA FEL injector unit.

· AES has provided JLab with a CAD file containing the most recent version of the 100 mA cryounit, including the implementation of the third harmonic cavity and power coupler.   

· Cavity processing and testing is scheduled to resume next week when the seals, flanges and facilities are scheduled to become available. 

· Engineering tasks on the beampipe designs and layout drawings are progressing according to available resources.  

WBS 8 (Instrumentation):

 The primary focus of this week was preparation of the Harvard Mass. General experiment in User Lab 1 and Ops support. We began with the search to find the source of the FEL amplitude noise. At the time, we suspected the HVPS ripple voltage was larger than spec. To confirm or dispel this possibility, we routed the Gun HVPS monitoring cables to the control room. We are still trying to determine the FEL noise source. 
    The problems we have had with the signal from the 1G dump have been solved with a new configuration.  The 1G03 Dump measurement was changed to reduce the noise within the system.  A new box was installed downstairs at the dump where power is supplied remotely and the capabilities to verify the calibration can be performed in the control room without an access.  Other changes were made to the system including additional filtering and various calibration points within the electronics downstairs.  The Charge/Dump Current Monitor Chassis was removed to include the power connections for the remote box and to clean up the wiring to eliminate noise being generated within the chassis. Now the focus on this system turns to matters of EPICS control. In resurrecting the system, we reprogrammed the cards with a working but less featured version of the firmware that the system used in the past. The IR-Demo could run 10 us pulses and so our alignment mode had a 60Hz/10us feature. The 10 kW FEL has a turn-on time of more than 30 us, so we are preparing a new version. We are also working to get the EPICS interface back to full working order. This will also be fixed in the next LPSS-AM card firmware version.  Special thanks to A. Grippo for developing a whole new user interface for the Drive Laser Pulse Controller Single-Shot Mode (DLPC-SS), that was produced overnight.  Additional LPSS hutch interlocks and their respective indicators were installed and checked out. The control room and User Lab Status Indicators were reinstated this week. Additional video requirements for recording this experiment including various cameras that were needed for looking at the experiment apparatus as well as video quads and distribution amplifiers to put all of the video signals were setup in the User Lab.  Several Microphones were setup for recording sound during the experiment, inside and out of the user hutch. The necessary low and high level LPSS certifications were completed and the experiment was ready to be run. 
    Progress is being made on the new BPM Electronics.  A design to incorporate the RF-DC Conversion circuitry onto the carrier board is in progress.  Also incorporated into this design is the placement of the on board Cold Fire Processor and all of the necessary components.  Part orders have been placed for the BPM electronics including enclosures and the processor connectors.  Connectors for the beam viewer chassis upgrade have been ordered as well. Fabrication of a 60 Hz notch filter box for the charge dump monitoring system is in progress.  Mechanical and fabrication drawings for the 4 Channel Solenoid Fail-safe Interface box have been signed off and delivered to EECAD. 
   Construction of the lab 3 terahertz hutch also continued this week. The last wall pieces were picked up from Hampton Sheet Metal this week, painted and installed. Once the doors are completed by Hampton Sheet metal, the final panel can go up above the door.  Fabrication also continued on the UV new sextuple magnet PS rack. Shelving for the first rack was adjusted and is ready installation of the controllers.  The EPICS read backs for the LPSS PLC upgrade are being sorted out. This involves all the values used in the current LPSS system along with incorporating the PLC status bits that can be used for debugging and viewing the overall health of the system. This is the initial stages of the data tables needed for the controller link aspect of the new PLC system. Also working on our system for storing documentation on the PLC memory as well as externally. A list of questions is being compiled for our meeting with Doug Smith that is coming up.

WBS 9 (Beam Transport):

Sextupole (SF) 

•   Fabrication is continuing at New England Techni-Coil. Hexagonal and Tee parts continue through the final machining before grinding and pole tip contouring. Coil winding has started again with shortened conductor ramp pieces. 

Replacement Chicane Dipoles GW) 

•   Fabrication is continuing at New England Techni-Coil. They potted the second coil. The fifth coil (out of 8) Is wound and being prepared for pressing. They glued the first Purcell gap glue down and are awaiting the epoxy cure. They are now anticipating shipping the first magnet next week. The second core is about to be complete. All the parts for the third and fourth cores are made except the 4 top and bottom plates. 

UV Line 

• 
We have agreed on a current ramp protocol for testing the 26 QX Quadrupoles so they that will match the capabilities of the Trim Card II to enable us to set the quads to field levels at the one part in 1000 level. 

• 
A third of seven electron beam transport sub-region’s assembly drawings was signed along with its girders. Two remaining regions being designed by the Engineering Group are well on their way. They will try to get the points to the Alignment group for next week’s bolt-hole location effort in the vault. The seventh is the wiggler zone, which awaits the drawings of the wiggler jaw mechanism which is in the bid evaluation process. 

• 
Advanced Energy Systems has completed the drawings for the sixth (GW Chicane) sub-region. We are generating the stand and cartridge points for them. Drawings are checked and they are in the process of getting them to us for signature. 
• 
We started ordering NEG Pumps and the valves. Bellows are next. 
UV Wiggler Progress 
•
No progress on the new Wiggler vacuum chamber.

WBS 10 (Wigglers):
Discussions continued on the UV wiggler modifications.  We expect to be able to request BAFO next week.

WBS 11 (Optics):
FEL mirrors: 
   We repeated the bonding procedure that gave such good results, and once again got a low aberration bond.  We also tried a variant of this procedure, applying pressure to the circumference of the mirror while the epoxy cured.  This worked reasonably well on a figured, but uncoated substrate (no power shift, 0.08 waves of astigmatism), but badly on a 3" DMA (2.8 micron HR bonded to a deformer).  The astigmatism axes were aligned with the water lines, similar to what we saw with a 2" deformer.  We are now checking our deformers by polishing the surface to measure the figure and look for astigmatism.  During the JTO Annual Program meeting (see below), I discussed our initial calorimetry results (~ 100 ppm) on our 1.06 micron HR with Al Ogloza (NAWC, China Lake).  Based on information he provided, subsequent discussions with the vendor for the 1.6 micron mirrors (who also coated the 1.06 micron mirrors) led to my decision to switch the high index dielectric from hafnia to tantala.  This does not affect the schedule, delivery is expected for the 3rd week of May.

 Other activities:
   Work this week concentrated on setting up the laser calorimeter in User Lab 6, where we will use it to qualify 1.06 micron coatings.  Work continues on qualification measurements for the advanced drive laser.  We completed the mechanical installation for the hutch in User Lab 1, and provided operations support for the first user experiment (Mass. General Hospital/Harvard Med.).  We also prepared for the next user experiment, for Dahlgren NSWC. We assisted in noise measurements on the drive laser and the FEL. 

I attended the final day of the JTO Annual Review and gave presentations on both the advanced drive laser and laser damage research the JTO is funding.

UV FEL
   The design of the optical cavity internals continued to progress.  Further discussions with the manufacturer of the He refrigerators revealed that they can't deliver the heat transfer rate we require.  We are pursuing discussions with other vendors.  Discussions on plasma cleaning techniques continues. The strongback for the second assembly was received, but went back to the Machine Shop.

Terahertz:

The spectrometer in lab 3 continues to function while work continued this week on the hutch.  Activities involving the hiring of a postdoc are still continuing.  We learned this week that the absolute THz power meter was shipped.






