## Sheet1
engineering for hall D through second year of operations |  |  | Paul Brindza
2000-10-31 |  | FY 02 | FY 03 | FY 04 | FY 05 | FY 06 | FY 07 | FY 08 | FY 09 | FY 10
engineering projects
magnet and Cryo |  | move | design | fab/repair | test | install | commission |  | run | run
Hall Mechanical systems |  |  |  | design | design/fab | install | install |  | run | run
Hall Electrical systems |  | Paul Brindza FY 05: design; Paul Brindza FY 06: install; Paul Brindza FY 07: install; Paul Brindza FY 09: run; Paul Brindza FY 10: run
Detector systems |  |  |  | design | design/fab | install | install | commission | run | run
Electronics |  |  |  | design | design/fab | install | install | commission | run | run
Installation |  | Paul Brindza FY 06: install; Paul Brindza FY 07: install
permanent Technical staff
lead Engineer | bar: FY 02 to Paul Brindza FY 10
lead Designer |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Designer | bar: Paul Brindza FY 03 to Paul Brindza FY 10
lead technician | bar: FY 02 to Paul Brindza FY 10
Mech tech. |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Mech. Tech |  |  |  | 0.5 | 1 | 1 | 1 | 1 | 1 | 1
Elec Tech | bar: Paul Brindza FY 04 to Paul Brindza FY 10
Elec Tech |  |  |  | 0.25 | 1 | 1 | 1 | 1 | 1 | 1
TDY Staff (JLAB)
Electrical Engineer (Physical Plant) | bar: Paul Brindza FY 05 to Paul Brindza FY 07
Electronics Engineer (Physics electronics) | bar: Paul Brindza FY 03 to Paul Brindza FY 08
Term Staff
Designer | bar: Paul Brindza FY 05 to Paul Brindza FY 07
Designer |  | Paul Brindza FY 03: 0.5; Paul Brindza FY 04: 1; Paul Brindza FY 05: 1; Paul Brindza FY 06: 1; Paul Brindza FY 07: 1
Welder | bar: Paul Brindza FY 06 to Paul Brindza FY 07
Mech tech | bar: Paul Brindza FY 06 to Paul Brindza FY 07
Elec tech | bar: Paul Brindza FY 06 to Paul Brindza FY 08
Elec tech | bar: Paul Brindza FY 06 to Paul Brindza FY 08
total by year |  | 2.5 | 6 | 8.75 | 12 | 16 | 16 | 11 | 8 | 8
Cost @ 75K$/FTE |  | 187.5 | 450 | 656.25 | 900 | 1200 | 1200 | 825 | 600 | 600
total cost to commission | 5418.75
asymptotic yearly cost | 600