## CDC
CDC Schedule Profile
Construction
Total
University Labor (man-weeks)
| professors |  | 65
| gradudate students |  | 160
| staff / grant |  | 290
| staff / other |  | 0
| Contributed University |  | 515
| Visiting Users |  | 0
| staff / project |  | 97
| undergraduate students |  | 310
| Hall D Technical Staff | Totals | 0
| Lead Designer | Tracking | 0 | designer at CMU
| Physicists (man-weeks) | Totals | 154
| Tracking | Tracking | 154
id | item | duration | duration | Quantity | unit/cost | cost | paid | paid univ | contri univ | scient | mech
| 2006-09-09 | days | weeks |  |  |  | student | staff |  |  | eng
110 | Procure & fabricate straws | 65.25 | 13.05 |  |  | 62.862
120 | Procure wire | 130.5 | 26.1 |  |  | 20
130 | Procure feedthroughs | 130.5 | 26.1 | 8000 | 0.01275 | 102
140 | Procure crimp pins | 130.5 | 26.1 | 10000 | 0.0015 | 15
150 | Procure HV cables | 130.5 | 26.1 |  |  | 11.15
160 | Procure signal cables | 130.5 | 26.1 |  |  | 30.111
170 | Procure gas connectors | 65.25 | 13.05 |  |  | 65
180 | Procure endplates | 174 | 34.8 | 2 | 20 | 60
190 | Procure support frame | 130.5 | 26.1 |  |  | 75
200 | Procure stand-offs | 87 | 17.4 |  |  | 5
210 | Procure carbon fiber shell (outer surface) | 130.5 | 26.1 | 1 | 3 | 3
220 | Procure fiber glass shell (inner surface) | 130.5 | 26.1 | 1 | 0.5 | 0.5
230 | Procure lucite (gas plenum) | 130.5 | 26.1 | 2 | 1.1 | 2.2
240 | Procure epoxy | 130.5 | 26.1 |  |  | 5
250 | Procure donut assemblies (Al, Delrin) | 130.5 | 26.1 |  |  | 0
260 | Procure preamps | 174 | 34.8 | 200 | 0.315 | 63 |  | 22$ per asic (2000) + 95$ per board (200)
270 | Procure calibration system |  |  |  |  | 88
150 | Procure LV cables | 130.5 | 26.1 |  |  | 16.157
160 | Alignment |  |  | 12 | 0.5 | 6
170 | rail bearings |  |  | 4 | 0.5 | 2
180 | HV distribution boards |  |  | 135 | 0.035 | 4.725
300 | Test straws | 10.88 | 2.176 | [5 empty] | 20
310 | Check wire quality | 21.75 | 4.35 |  |  |  |  | 17
320 | Check feedthroughs | 21.75 | 4.35 | [5 empty] | 20
330 | Check crimp pins | 10.88 | 2.176 | [5 empty] | 20
340 | Check endplates | 21.75 | 4.35 |  |  |  |  | 20
350 | Test On-chamber electronics | 43.5 | 8.7 | [5 empty] | 35
350 | [9 empty] | 44
410 | Clean endplates and components | 10.88 | 2.176 |  |  |  | 10
420 | Construction setup | 65.25 | 13.05 |  |  |  | 20
420 | [10 empty] | 20
430 | Cut all straws to length | 87 | 17.4 |  |  |  | 20
430 | [7 empty] | 20
440 | Insert straws into frame | 130.5 | 26.1 |  |  |  | 50
440 | [7 empty] | 20
450 | Chamber stringing | 130.5 | 26.1 |  |  |  | 150
450 | [7 empty] | 20
460 | Gas system installation | 65.25 | 13.05 |  |  |  | 20
460 | [8 empty] | 50
470 | Electronics installation | 130.5 | 26.1 |  |  |  | 30
470 | [9 empty] | 27
470 | [8 empty] | 20
480 | Mount signal connectors | 21.75 | 4.35 |  |  |  | 10
490 | Attach shell | 10.88 | 2.176 | [5 empty] | 20
500 | Complete gas system | 10.88 | 2.176 | [5 empty] | 50
600 | Mechanical tests | 43.5 | 8.7 | [5 empty] | 40
610 | HV tests | 43.5 | 8.7 | [5 empty] | 40
620 | Signal tests | 65.25 | 13.05 | [5 empty] | 40
630 | Resolution studies | 43.5 | 8.7 | [5 empty] | 40
630 | [9 empty] | 44
640 | Cross talk studies | 21.75 | 4.35 | [5 empty] | 40
650 | Magnetic field tests | 21.75 | 4.35 | [5 empty] | 40
700 | Shipping | 32.63 | 6.526 |  |  | 5 |  |  | 40
| Total |  |  |  |  | 641.705 | 310 | 97 | 515 | 115 | 20